## Summary
MDR Phase 2 - Enhancements
Sl. No. | Feature Complexity | No. of items | No. of Person Days | Amount (INR)
1 | Simple (No color) | 17 | 10 | 20000
2 | Moderate (Orange) | 6 | 24 | 40000
3 | Complex (Yellow) | 4 | 25 | 40000
4 | Misc | 3
| Total | 30 | 59 | 100000

## MDR Phase 2 - Enhancements
Date | Module | Issue | Priority | Duration in days | Bug/Mod/Enhancement | Status (open/closed) | Comments
2016-01-20 | Login | Please sign in --> <Name of the application> To be provided by Sri Alwar. Use "Yoga Text Resources" for now. |  |  | N/A
2016-01-20 | Login | Include labels. Email ID and Password. |  |  | Mod | Closed
2016-01-20 | App | Successfully Saved The User Details. --- common issue capitalization of each word. |  |  | Mod | Closed
2016-01-20 | App | Name of the application along with the organization name. |  |  | N/A
2016-01-20 | App | Link to the organization website either in the header or in the footer. |  |  | Mod | Closed
2016-01-20 | App | (reduce blank space) |  |  | Mod | Open
2016-01-20 | App | Digital Repository of Medical Manuscripts and Books of Karnataka Sponsored by Department of Ayush(Karnataka) Department of Health and Family Welfare Government of Karnataka (As per recommendation of the Karnataka Knowledge Commission) -----The above information should be removed from the system. |  |  | Mod | Closed
2016-01-20 | App | Display is fine only when the window is maximized. When the window size is altered, the display becomes messy and unusable. |  |  | Mod | Open
2016-01-20 | App | Auto complete field values must be alphabetically sorted. Avoid duplicates. |  |  | Mod | Closed
2016-01-20 | App | submit --> Submit (multiple occurrances) |  |  | Mod | Closed
2016-01-20 | App | Provide an option to reset the radio buttons, when a wrong selection is made and the right value is not known. | Low | 0.5 | Enhancement | Open | Required
2016-01-20 | App | Find All --> List All |  |  | Mod | Closed
2016-01-20 | App | New field -- Upload status ( None, Incomplete, WIP, Partial, Full). WIP - Upload is in progress. We have the required material. Full - All the images for the entire work have been uploaded. Partial - All the images for the required extract of the work have been uploaded. Incomplete - Only a few images have been uploaded. Eg. We have just the cover page. We do not have the required material. None - We do not have the required material. | Medium | 0.5 | Enhancement | Open | Required
2016-01-20 | App | Reduce the space between the label and the field. Example - Summary, TOC and other fields in new doc page. |  |  | Mod | Open
2016-01-20 | App | Period of The Author --> Period of the Author. In the labels, "of" and "the" are not be capitalized when they are not the first word. |  |  | Mod | Closed
2016-01-20 | App |  |  |  | N/A
2016-01-20 | Dashboard | DashBoard --> Dashboard |  |  | Mod | Closed
2016-01-20 | Dashboard | administrator --> Administrator |  |  | Mod | Closed
2016-01-20 | Dashboard | Blank page for all roles except administrator. Same page for all roles as of now. Later workflow will be implemented. | Low | 0 | Major Enhancement | Open | Required. These pages will show the respective pool and generic pool contents in workflow
2016-01-20 | Dashboard | The navigation blocks are clickable - but no action. They should open the appropriate Search page. | Low | 0 | Enhancement | Open | Required
2016-01-20 | Dashboard | Workflow Summary - Not a person but an activity. Nomenclature to be changed to Scholar - Creation [Not Required] Reviewer - Review [ The unpublished work is being considered for publishing and for that the review is going on. Swap with Verification] Publisher - Publishing [ The unpublished work is being taken up for publishing ] Published - Published [Default] [For all documents that were made available in print form] Verifier - Verification [ The unpublished work has been now printed and it is being verified. Swap with Review] Translator - Translation [ The work is now being translated ] Not Assigned - Not Assigned The entries made in the system would be reviewed through offline communications. i.e., by sending a mail to the reviewer to check certain entries. | Low | 0.5 | Enhancement | Open | Need final nomenclature
2016-01-20 | Dashboard | User manual will have the details. FAQ option to be taken out. |  |  | Mod | Closed
2016-01-20 | Dashboard | Records Summary. Fix the nomenclature. Menu has "Documents". If that is fine, use that term. Records Summary --> Documents Summary Record details --> Document Details Number of Records (in the navigation block) --> Documents |  |  | Mod | Closed
2016-01-20 | Dashboard | Record details == remove |  |  | Mod | Closed
2016-01-20 | Role | Create Role --> New Update Role --> List All (Since all the other menu options are given this way -- for the sake of consistency). |  |  | Mod | Closed
2016-01-20 | Lookup Management | Lookup Management --> Value Lists Maintain consistency in the title of the pages and the label for the search field. |  |  | Mod | Open | Need info.
2016-01-20 | Reports | TO BE TAKEN UP LATER. |  |  | N/A
2016-01-20 | My Account | Reset Password should not be under My Account. Ideally it should be made available along with the options for edit and delete within search page. For now, it can be moved and be shown as the last sub-menu option under User menu. |  |  | Mod | Closed
2016-01-20 | User | Option 1. While creating the user, enable setting a default role (new field - single value from the list). This should be used while logging in. Option 2. If the user has administrator access, make that the default role on logging in (if the new field is not introduced). Sri Alwar to confirm. Option 3. For now --- assign only one role. | Later |  | N/A
2016-01-20 | User | Search -- Pop up message "Please enter any value to search" --> "Please enter some value to search". |  |  | Mod | Closed
2016-01-20 | User | Search -- Telephone should not be the first field. It should be the last field. |  |  | Mod | Closed
2016-01-20 | Tags | List All option is required. | Low | 0 | Enhancement | Open | Required
2016-01-20 | Bundle | TO BE TAKEN UP LATER. |  |  | N/A
2016-01-20 | Documents | Instead of New sub-menu option, provide "New Book", "New Article" and "New Document". | Medium | 2 | Major Enhancement | Open | Required
2016-01-20 | Documents | The message "Please enter at least one field" is showing the three fields along with ID field in red color. Remove the ID field from this list. Only one of the other three are mandatory. |  |  | Mod | Closed
2016-01-20 | Documents | Remove the tip. Include it as a tool tip as given for author name with "i" info icon. |  |  | Mod | Closed
2016-01-20 | New Document | Specific Category field overlaps with the next field. |  |  | Bug | Closed
2016-01-20 | Specific Category | TO BE DISCUSSED INTERNALLY. | Medium |  | Major Enhancement | Open | Need clear information
2016-01-20 | Tag section | To be aligned properly. The labels are not placed before the appropriate fields. |  |  | Bug | Closed
2016-01-20 | Specific Contribution | first label is missing. |  |  | Bug | Closed
2016-01-20 | Information | TO BE DISCUSSED INTERNALLY. "Information" --> "Basic Info." |  |  | Mod | Closed
2016-01-20 | Author | TO BE DISCUSSED INTERNALLY. "Author" --> "Author Info." |  |  | Mod | CLosed
2016-01-20 | Frames | TO BE DISCUSSED INTERNALLY. "Frames" --> "Images" |  |  | Mod | Closed
2016-01-20 | Others | TO BE DISCUSSED INTERNALLY. "Others" --> "Additional Info." |  |  | Mod | Closed
2016-01-20 | Order of tabs | TO BE DISCUSSED INTERNALLY. Can the Frames or Images tab be made the last tab so that we can click on submit after uploading? The initial tabs will all be info related. | Low | 0 | Enhancement | Open | Required
2016-01-20 | Frames | "Click on the BROWSE button to browse the images you want to upload.Open the destination folder and select the images. Then click on UPLOAD button and wait for the response to upload the images before clicking the SUBMIT button in last tab." --> "Click the BROWSE button to select the images that you want to upload. Click the UPLOAD button and wait for the confirmation message. Then click the SUBMIT button in last tab to save the uploaded images." |  |  | Mod | Closed
2016-01-20 | Frames | Is there a way to change the order of the images | Medium | 5 | Major Enhancement | Open | Required
2016-01-20 | Frames | How to change the orientation? The images seem to be rotated. | Medium | 4 | Major Enhancement | Open | Required
2016-01-20 | Price (INR) | Split it as two fields. Price and Currency. Provide Look up for Currency | Low | 0.5 | Enhancement | Open | Required
2016-01-20 | Available in Print | Save the selected value. |  |  | Bug | Closed
2016-01-20 | Language | TO BE DISCUSSED INTERNALLY. Whether multi-value field is required rather than creating combinations. Advantage of multi-value would be all docs having sanskrit would get listed when we choose sanskrit. Multi-value field. | High | 5 | Major Enhancement | Open | Required
2016-01-20 | Article | Article -- Reduce the blank space so that we do not have to scroll down to click on the buttons. |  |  | Mod | Closed
2016-01-20 | Article | Remove "It is in English" radio buttons. Always show the other two fields as shown for books. |  |  | Mod | Closed
2016-01-20 | Subject | TO BE DISCUSSED INTERNALLY. "Subject" --> "Type of Yoga". Multi-value selection allowed. | High | 3 | Major Enhancement | Open | Required
2016-01-20 | Article | TO BE DISCUSSED INTERNALLY. (Specific Category - multi-value selection field. The values need to be finalized). | High | 3 | Enhancement | Open | Required
2016-01-20 | Article | TO BE DISCUSSED INTERNALLY. "Name so fields covered" --> "Names of fields covered" |  |  | Bug | Closed
2016-01-20 | Article | TO BE DISCUSSED INTERNALLY. Online Journal / Publication, Journal / Magazine / Others --> Online Material, Printed Material, Unpublished work. | Medium |  | Enhancement | Open | Need clear information
2016-01-20 | Article | Remove Published field with Yes and No radio buttons in the Others tab. Always show publication related fields as shown in books page. |  |  | Mod | Closed
2016-01-20 | Documents | Author's Life History --> Author's Biography |  |  | Mod | Closed
2016-01-20 | NMM | TO BE DISCUSSED INTERNALLY. NMM --> "????" Sri Alwar to clarify. (National Manuscript Mission) |  |  | N/A
2016-01-20 |  |  |  |  | N/A
2016-01-20 | Digitized by | Tool Tip. The content is not visible since it is lengthy. "Start typing the digitizer name from the begining in the auto-complete field and you will get the related digitizer list if present in the system.Then select the proper digitizer from the list." --> "Start typing the name and select the required entry from the list of available entries". |  |  | Mod | Closed
2016-01-20 | Publisher Search | TO BE TAKEN UP LATER. |  |  | N/A
2016-01-20 | Merge Manuscript | TO BE TAKEN UP LATER. |  |  | N/A
2016-01-20 | View Documents | Advanced Search For Documents --> Search Documents for Viewing |  |  | Mod | Closed
2016-01-20 | Search | Advanced Search For Documents --> Search Documents for Viewing/Editing |  |  | Mod | Closed
2016-01-20 | workflow status | Not Assigned - Not Assigned Unselected - Not Assigned Under_Scholar - Creation [ Not required] Under_Reviewer - Review Under_Publisher - Publishing Published - Published Under_Verifier - Verification Under_Translator - Translation |  |  | N/A
2016-01-20 | Search | TO BE DISCUSSED INTERNALLY/ Having Content… --> use the appropriate field name. |  |  | Mod | Closed | 1.Summary,2:Table Of Contents,3:To Subject,4:Uniqueness of Work Fixed
2016-01-20 | Frames | "Unable to upload due to some issue in the PDF" --> In that specific case when no file is selected "Select a file for upload using the Browse button". |  |  | Bug | Closed
2016-01-20 | Frames | "Unable to upload due to some issue in the PDF" --> "Unable to upload the file. Make sure that the file is not in use." (as it could also be an image and this error comes up when the file is open. |  |  | Bug | Open | Not reproducible. Need all cases.
2016-01-20 | Home page | Change Implemented by Sanskriti Foundation , Karnataka . Powered by Indven Technologies to Implemented by Samskriti Foundation, Karnataka . Powered by Indven Technologies |  |  | Mod | Closed
2016-01-20 | Frames | Unable to see frames in "View" However, if I search an entry and click on 'View' , even though I see the thumbnail images of the uploaded images on the left part of the main page, whenever I click on any image, the image does not get loaded for viewing. The main area, where we are supposed to see the image just looks like it is loading forever. |  |  | Bug | Closed
2016-01-20 | Hierarchical Structure | TO BE DISCUSSED INTERNALLY. A multi-tier field to be introduced. | High | 4 | Major Enhancement | Open | Required
2016-01-20 | Error message | "Already one authore fields are blank" --> "A set of blank Author fields is already available" (my preferred option). |  |  | Bug | Closed
2016-01-20 | TOC | There seems to be some limitation (around 3.5K characters including spaces) for the Table of Contents field. Kindly increase the number of characters to 5.5 K including spaces. |  |  | Mod | Closed
2016-01-20 | Author's Biography / history | The current size seems to be 1.5K characters with spaces for Author's history. It could be increased to 3K characters with spaces. |  |  | Mod | Closed
2016-01-20 | Search | icon for type of doc in search results | Medium | 0.5 | Enhancement | Open | Required
2016-01-20 | Search | Remove type column from search results | Medium | 0.5 | Enhancement | Open | Required
2016-01-20 | app | Error should remain and not vanish |  |  | Bug | Closed
2016-01-20 | language | Check and remove the Unicode field from languages. | Low | 0 | Enhancement | Open | Required. We need this code for workflow translation functionality
2016-01-25 | New Document | Book name - size restriction - Allow upto 150 character -- For example, this one is 121 -- "Yoga Sutras of Patanjali: An Analysis of the Sanskrit with Accompanying English Translation (Studies in Indian tradition)" |  |  | Mod | Closed
2016-01-25 | Documents | Author's Life History --> Author's Biography … Should be a text area and not a text box. | Medium | 0 | Enhancement | Open | Required
2016-01-25 | Books | For commentaries on works like Patanjali's Yoga Sutra, the commentators also are equally important. So a field to capture the Commentator's Biography is required as a text area. | Medium | 1 | Enhancement | Open | Required
2016-01-25 | Books | Unable to store the second commentator's name for "Yoga Sutras of Patanjali: An Analysis of the Sanskrit with Accompanying English Translation" | Medium | 3 | Major Enhancement | Open | Required
2016-02-01 | Audit Trail | In case we want to sort based on the data-entry date or filter based on the user who entered the record, we should be able to get this info. Needs to be done for all operations in the system. Creation/Modified/Deletion/Purging/Archiving | Low | 7 | Major Enhancement | Open | Required
2016-02-02 | Subject field | I was able to create the required tiered level for the field - Subject. In the List All option, please do the following: 1. Include Parent Subject Name as another column 2. Sort the list based on Subject 3. Prevent duplicates if the subject name and parent subject name is the same. (I notice that there are two bhakti yoga. I will check those and delete one after ensuring that all books use only the other one). 4. A general question -- It is common practice to let users sort the columns by clicking on the column name and also allow them to choose the required columns when there are more columns. Will you be able to implement that for the lists - especially the search documents result would require this feature. | Medium | 1 | Enhancement | Open | Required
2016-02-02 | Search | We intend to have more people involved in generating the content. We need to be able to search based on the data entry operator who created the record and the date. Please include these fields in Search Documents for Editing page: Record created by, Record created on, Record updated by Record updated on | Low | 0 | Enhancement | Open | Required
2016-02-02 | Mass Upload | Bulk uploading of PDFs and Images to save uploading time | Medium | 5 | Enhancement | Open | Required
2016-02-02 | Image Tagging | While a book could deal with multiple subjects (say bhakti yoga, jnana yoga, etc.), we notice that there are specific chapters on individual subjects. In such a case, it would be required to tag the images associated with those chapters with the appropriate subject. | High | 10 | Enhancement | Open | Required
2016-02-03 | Deletion and Back up | 1. We need to have a separate access for deletion. Administrator will be the only role which will have deletion access by default. For other roles, the administrator will have to enable access explicitly for deletion only when required and revert it when the work is done. 2. Are you doing soft delete retaining the record in DB? 3. What is the backup plan? If something goes wrong, can we revert to some backup data? How many days earlier data will be available? | Medium | 3 | Enhancement | Open | Required
2016-02-11 | Uploading data of mss / booksss / articles without images | There should be option to upload only the data of data of mss / booksss / articles without images (as in the MMS segment of FRLHT MDR). When search is conducted, the results should give an indicator as to whether the images of that document is available in the database or not, which will enable the user to further use the database accordingly | Medium | 0 | Enhancement | Closed | Required. Currently image uploads are optional and there is a column in search which says if the Frames are available or not